## 🧮 Effort Calculator
MIGRATION EFFORT CALCULATOR — DYNAMIC FORMULA VERSION
Azure SQL MI → AWS Aurora PostgreSQL ¦ Schema + Data + ETL ¦ Devin AI + GitHub Copilot
★ Yellow = count input ¦ Orange = base rate (editable) ¦ Blue = AI saving % (editable) ¦ Grey = auto-calculated
| Object / Activity | Count ★ (your input) | Base Rate (hrs/unit) ✎ | AI Saving % ✎ | AI-Adj Rate =D×(1−E%) | Subtotal Hrs =C×F | SDLC +25% =G×0.25 | Risk +10% =G×0.10 | TOTAL HOURS =G+H+I
A. SCHEMA MIGRATION
Orange cells (column D) = base rate in hrs/unit — change this if your team benchmarks differ. Blue cells (column E) = AI saving % — change if Devin/GHCP performs differently on your codebase. Column F recalculates instantly: F = D × (1 − E/100).
| Tables (SCT auto-convert + DBA review) | 500 | 0.4 | 80
| Views (SCT + manual fix for T-SQL functions) | 250 | 1.5 | 65
| Indexes (clustered → heap + B-tree strategy) | 200 | 0.5 | 50
| SPs — Simple CRUD (Devin autonomous batch) | 120 | 0.67 | 75
| SPs — Business Logic (Devin + full DBA review) | 105 | 1.5 | 65
| SPs — Complex (DBA manual rewrite + GHCP) | 45 | 4 | 40
| SPs — CLR Objects (architecture redesign) | 30 | 8 | 20
| Functions — Scalar + Table-Valued | 150 | 1 | 65
| Triggers (simplify first, then convert) | 75 | 2 | 45
| SQL Agent Jobs (→ pg_cron / Lambda) | 50 | 2 | 60
| Security Roles & Logins (Devin RBAC scripts) | 40 | 0.5 | 65
Devin Fine-Tuning is a FIXED cost — 80 hrs mandatory before batch SP conversion. Column D is editable if your fine-tuning scope differs. No AI saving applied (E = 0%).
| Devin Fine-Tuning (FIXED — mandatory gate before batch SP conversion) | Fixed | 80 | 0
★ SCHEMA MIGRATION TOTAL
B. DATA MIGRATION
Column C = volume (GB or weeks or count). Column D = effort rate per unit. Column E = AI saving %. Column F = D × (1 − E/100) — updates live when you change D or E.
| App DB — Tier 1 size (GB) | 2000 | 0.004 | 20
| App DB — CDC Monitoring (weeks) | 12 | 8 | 30
| Warm History — Tier 2 (GB) | 12000 | 0.003 | 40
| Cold Archive — Tier 3 (GB) → S3 + Athena | 35000 | 0.001 | 50
| Tables to Validate (count, all tiers) | 500 | 0.25 | 70
| Cutover Rehearsals (count — min 2) | 2 | 32 | 20
| DMS Infrastructure Setup (fixed, enter 1) | 1 | 24 | 40
★ DATA MIGRATION TOTAL
C. ETL MIGRATION (ADF → Apache Airflow + PySpark)
Column C = number of ADF objects of that type. Column D = base hrs/object (editable — adjust to your team velocity). Column E = AI saving % (editable). Column F recalculates: F = D × (1 − E/100).
| ADF Copy Activity pipelines (Devin → Airflow DAG) | 45 | 2 | 65
| ADF Stored Proc Activity pipelines (Devin) | 20 | 1.5 | 65
| ADF REST / Web Activity pipelines (Devin) | 15 | 3 | 55
| ADF Mapping Data Flows — Simple (Devin → PySpark) | 30 | 4 | 55
| ADF Mapping Data Flows — Complex (GHCP + developer) | 20 | 8 | 40
| ADF Custom .NET Activities (manual rewrite + GHCP) | 10 | 16 | 35
| ADF Azure-specific pipelines (ADLS / Synapse redesign) | 8 | 24 | 20
| Azure Functions (→ AWS Lambda / Step Functions + GHCP) | 15 | 8 | 40
| ETL Parallel Validation (ADF vs Airflow output diff) | 50 | 1 | 55
| MWAA + Glue Infrastructure Setup (enter 1 = fixed) | 1 | 24 | 50
★ ETL MIGRATION TOTAL
D. TESTING, UAT & PROJECT MANAGEMENT
Testing and PM hours are calculated as % of the combined Schema+Data+ETL total — no count to enter. Column D = % of combined total (editable). Column E = AI saving % (editable). Column F = D% × combined × (1−E/100) = effective hrs rate.
Combined Base = Schema + Data + ETL totals (used for % calculations below)
| Activity | (auto) | % of Combined ✎ | AI Saving % ✎ | Effective Hrs =Combined×D%×(1−E%) | Subtotal Hrs | SDLC +25% | Risk +10% | TOTAL HOURS
| Unit + Integration Testing (SP + ETL functional tests) | % based | 18 | 55
| Performance Benchmarking (EXPLAIN ANALYZE + tuning) | % based | 8 | 35
| Regression Testing — Ordering Application | % based | 12 | 30
| Regression Testing — Billing Application | % based | 15 | 30
| UAT — Ordering (business users) | % based | 10 | 5
| UAT — Billing (business users + billing SME) | % based | 14 | 5
| Defect Management & Fix Cycles | % based | 15 | 40
| Project Management & Governance | % based | 18 | 25
| Knowledge Transfer & Training | % based | 8 | 40
★ TESTING + PM TOTAL
★ GRAND TOTAL — ALL STREAMS WITH ALL BUFFERS
Total Days (Grand Total Hours ÷ 8)
Calendar Weeks (Total Hours ÷ 240 assuming 6-person team × 40 hrs/week)
SUMMARY: HOURS BY STREAM
| Stream | AI-Adj Subtotal | SDLC +25% | Risk +10% | Total Hours | Total Days
🔵 Schema Migration
🟢 Data Migration
🟣 ETL Migration
🔬 Testing + PM
★ GRAND TOTAL
HOW THE FORMULAS CHAIN: C (count) × F (AI-adj rate) = G (subtotal) → G × 0.25 = H (SDLC) → G × 0.10 = I (Risk) → G+H+I = J (Total) ¦ F = D × (1 − E/100) ¦ Changing D or E in any row instantly recalculates F, G, H, I, J and all totals.

## 📐 Legend & Rates
COLUMN LEGEND & DEFAULT RATE DERIVATION
Column C — Count input | Yellow cell | Enter your inventory count or volume | Editable by user | All rows
Column D — Base rate | Orange cell | hrs/unit before any AI saving applied | Editable — change if team benchmarks differ | All rows
Column E — AI saving % | Blue cell | % effort saved by Devin + GHCP (0–100) | Editable — change based on your AI tool performance | All rows
Column F — AI-adj rate | Grey formula |  | Auto-calculated — never edit directly | All rows
Column G — Subtotal hrs | Grey formula |  | Auto-calculated | Section A/B/C rows
Column H — SDLC buffer | Gold formula |  | Auto-calculated | All rows
Column I — Risk buffer | Orange formula |  | Auto-calculated | All rows
Column J — Total hours | Coloured formula |  | Final output — hours with all buffers | All rows
DEFAULT RATES — SOURCE AND DERIVATION
Object / Activity | Default Rate (D) | Default AI % (E) | AI-Adj Rate (F=D×(1-E%)) | Source | Notes
Tables (SCT) | 0.4 | 80% | 0.08 | AWS telecom case study | SCT 95% auto. DBA reviews DDL. 0.08 hrs = ~5 min/table.
Views | 1.5 | 65% | 0.525 | Industry benchmark | 35% need manual T-SQL fix. GHCP suggests PG equivalents.
Indexes (clustered→B-tree) | 0.5 | 50% | 0.25 | Telecom case study | DA designs strategy, Devin generates DDL, DBA reviews.
SPs — Simple CRUD | 0.67 | 75% | 0.168 | Nubank/Devin: 10 min/SP | 10 min/SP after fine-tuning. Devin autonomous.
SPs — Business Logic | 1.5 | 65% | 0.525 | Devin benchmark | 25 min/SP AI-adjusted. Full DBA PR review mandatory.
SPs — Complex | 4 | 40% | 2.4 | Industry: 4–6 hrs manual | 90 min/SP with GHCP. Dynamic SQL, cursors, TempDB.
SPs — CLR Objects | 8 | 20% | 6.4 | Architecture redesign | No PG equivalent. DA designs, DBA implements.
Functions | 1 | 65% | 0.35 | SCT + Devin benchmark | SCT handles 70%. Devin fixes rest. 0.35 hrs avg.
Triggers | 2 | 45% | 1.1 | Telecom case study | Simplify first. Devin converts simple. 1.1 hrs avg.
SQL Agent Jobs | 2 | 60% | 0.8 | Devin batch benchmark | → pg_cron / Lambda / Step Functions. 0.8 hrs/job.
Security Roles | 0.5 | 65% | 0.175 | Devin RBAC scripts | Devin generates RBAC. Security team flat 8 hr review.
Devin Fine-Tuning | 80 | 0% | 80 | Nubank precedent | FIXED 80 hrs. Doubles Devin accuracy post-tuning.
App DB — DMS (per GB) | 0.004 | 20% | 0.003 | DMS sizing data | CDC monitoring is main cost (separate weeks row).
CDC Monitoring (per week) | 8 | 30% | 5.6 | DBA norms | 5.6 hrs/week with GHCP dashboards. 12–16 weeks telecom.
Warm History (per GB) | 0.003 | 40% | 0.0018 | BCP+COPY benchmarks | BCP export + S3 + Aurora COPY. Devin scripts.
Cold Archive (per GB) | 0.001 | 50% | 0.0005 | Snowball logistics | Active effort very low per GB. Snowball does transfer.
Table Validation (per table) | 0.25 | 70% | 0.075 | Devin auto-gen | Row count + checksum + FK. Devin generates all SQL.
Cutover Rehearsal (each) | 32 | 20% | 25.6 | Industry standard | Full team 32 hrs. Minimum 2. GHCP generates runbook.
DMS Infrastructure (fixed) | 24 | 40% | 14.4 | AWS setup baseline | VPC, endpoints, CloudWatch. Fixed regardless of DB size.
ADF Copy Activity | 2 | 65% | 0.7 | Devin DAG gen | Devin reads ADF JSON → Airflow DAG + tests. ~42 min.
ADF Stored Proc Activity | 1.5 | 65% | 0.525 | Devin benchmark | → Airflow PostgresOperator. Fast conversion.
ADF REST/Web Activity | 3 | 55% | 1.35 | Devin benchmark | → Airflow HttpOperator. 1.35 hrs avg.
ADF Data Flow — Simple | 4 | 55% | 1.8 | Devin→PySpark bench | Filter, derive, sort, aggregate. Devin converts.
ADF Data Flow — Complex | 8 | 40% | 4.8 | GHCP pair coding | Billing flows = complex. Window fns, SCD logic.
Custom .NET Activity | 16 | 35% | 10.4 | Manual rewrite | Complete Python/Lambda rewrite. GHCP reduces typing.
Azure-specific pipelines | 24 | 20% | 19.2 | Redesign required | ADLS/Synapse deps. High uncertainty. Flag early.
Azure Functions | 8 | 40% | 4.8 | GHCP benchmark | → Lambda/Step Functions. Azure SDK dependency risk.
ETL Parallel Validation | 1 | 55% | 0.45 | Devin diff scripts | ADF output vs Airflow output row-level comparison.
MWAA + Glue Setup (fixed) | 24 | 50% | 12 | AWS setup baseline | Infrastructure setup. Fixed cost (enter count=1).