## ✏️ SME Input
📋 INSTRUCTIONS: Fill in ORANGE cells only. S.No = sequence number ¦ VAST ID = your VAST system ID ¦ APP ID = application code. Dropdown cells show ▼ — click to select. Leave rows blank if not used.
IDENTIFIERS |  |  | APPLICATION & WAVE |  | DATABASE & OBJECT INVENTORY | [9 empty] | ETL & REPORTING |  |  | INFORMATICA & REPLICATION |  |  |  | NOTES
S.No | VAST ID | APP ID | Application Name | Wave / Release | DB Size (GB) | No. of Tables | No. of Stored Procs | No. of Views | No. of Triggers | SQL Agent Jobs | Linked Servers | CLR Objects | SSIS Packages | SSRS Reports | Informatica Workflows/Jobs (No workflow change — count) | SSIS Complexity | SSRS Strategy | Informatica Job Count | Replication Articles (Trans+Merge) | Snapshot Publications | Replication Type | SME Notes / Risks
⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ▼ Select | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ▼ Select | ▼ Select | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ▼ Select | Free text
TOTALS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0

## 📋 App Effort Detail
Formulas auto-calculate from SME Input sheet values. Orange = SME editable input. Green = calculated output. Hours = Days × 8. AI saving applied per role. Contingency = AI-adj × (1 + buffer%).
APP IDENTITY |  | DATABASE PROFILE |  |  |  |  | SQL OBJECT INVENTORY | [5 empty] | ETL & REPORTING |  |  | EFFORT TOTALS (hours) | [9 empty] | INFORMATICA EFFORT (hrs) |  |  |  |  | ENVIRONMENT BREAKDOWN — Data & ETL (hrs) | [5 empty] | TOTAL BY ENV (hrs) |  |  | APPLICATION IDENTIFIERS
Application Name | Tier (Auto) | DB Size (GB) | Tables | Stored Procs | Views | Triggers | SQL Agent Jobs | Linked Servers | CLR Objects | SSIS Packages | SSRS Reports | Informatica Workflows/Jobs (No workflow change — count for JDBC) | SSIS Complexity | SSRS Strategy | Wave | Gross Hours | AI-Adj Hours | Hours w/ Contingency | [7 empty] | Informatica Job Count | Inform. Dev hrs | Inform. Test hrs | Inform. Prod hrs | Inform. Total hrs | Data Dev hrs | Data Test hrs | Data Prod hrs | ETL Dev hrs | ETL Test hrs | ETL Prod hrs | Total Dev hrs | Total Test hrs | Total Prod hrs | S.No | VAST ID | APP ID
Label/Formula | Label/Formula | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | Formula | Formula | Formula | [7 empty] | Ref SME | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Ref SME | Ref SME | Ref SME
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 📊 Dashboard
29 Applications ¦ SSIS→AWS Glue ¦ Informatica: No Change ¦ 9-Month Rolling ¦ GHCP + Devin AI
PROGRAMME ASSUMPTIONS (Orange = editable inputs)
Hours per Day (basis) | 8
Programme Timeline (months) | 9
AI Saving % — Schema/Code/DBA | 30
AI Saving % — ETL (SSIS→Glue) | 25
AI Saving % — SSRS / BI Work | 20
AI Saving % — Testing & QA | 20
Contingency Buffer % | 15
Parallel Apps in Flight (wave) | 4
PROGRAMME TOTALS (Live — recalculates from App Effort Detail)
Total Apps | Total DB (GB) | Gross Hours | AI-Adj Hours | Hours w/ Conting. | FTE Equiv. | Days Equiv.
29 | 0 | 0 | 0 | 0 | 0 | 0
EFFORT BY ROLE (Hours)
Role | Gross Hours | AI Saving % | AI-Adj Hours | With Contingency | FTE Equiv. | % of Total
Solution Architect | 0 | 30 | 0 | 0 | 0 | 0%
DBA / Database Engineer | 0 | 30 | 0 | 0 | 0 | 0%
ETL Developer (SSIS→Glue) | 0 | 25 | 0 | 0 | 0 | 0%
SSRS / BI Developer | 0 | 20 | 0 | 0 | 0 | 0%
AWS Infra / DevOps | 0 | 30 | 0 | 0 | 0 | 0%
QA / Test Engineer | 0 | 20 | 0 | 0 | 0 | 0%
Project Manager | 0 | 30 | 0 | 0 | 0 | 0%
TOTAL | 0 |  | 0 | 0 | 0 | 0%
LEGEND
● Orange = Editable assumption — change to model different scenarios
● Blue = Locked programme parameter
● Green = Calculated output (hours incl. AI saving + contingency)
INFORMATICA EFFORT (Connection update per job × 3 environments)
Total Jobs | Dev (hrs) | Test (hrs) | Prod (hrs) | All Envs (hrs)
0 | 0 | 0 | 0 | 0
TOTAL EFFORT BY ENVIRONMENT (All layers — hours)
Development (Dev RDS) | Test / UAT (Test RDS) | Production (Prod RDS) | Total All Environments
0 | 0 | 0 | 0
REPLICATION INVENTORY SUMMARY
Apps w/ Replication | Total Articles (Trans+Merge) | Total Snapshot Pubs | Transactional | Merge/Snapshot | None
1 | 0 | 0 | 0 | 0 | 0

## 🔍 App Pivot View
APPLICATION DRILL-DOWN VIEW — Select an application to see full effort breakdown
SELECT APPLICATION:
▼ Click C5 to select an application from the dropdown. The list updates automatically as you enter app names in the SME Input sheet.
Matched Row (ref): | 8
APPLICATION PROFILE
Application Name | 0
Migration Tier
DB Size (GB) | 0
Wave / Release | 0
SSIS Complexity | 0
SSRS Strategy | 0
SQL OBJECT INVENTORY
Tables | 0
Stored Procedures | 0
Views | 0
Triggers | 0
SQL Agent Jobs | 0
Linked Servers | 0
CLR Objects | 0
SSIS Packages | 0
SSRS Reports | 0
Informatica Workflows | 0
EFFORT BREAKDOWN (HOURS)
Role | Gross Hours | AI Saving % | AI-Adj Hours | w/ Contingency
Solution Architect | 0 | 30 | 0 | 0
DBA / DB Engineer | 0 | 30 | 0 | 0
ETL Dev (SSIS→Glue) | 0 | 25 | 0 | 0
SSRS / BI Developer | 0 | 20 | 0 | 0
AWS Infra / DevOps | 0 | 30 | 0 | 0
QA / Test Engineer | 0 | 20 | 0 | 0
Project Manager | 0 | 30 | 0 | 0
TOTAL (this app) | 0 |  | 0 | 0
APPLICATION SUMMARY TOTALS
Gross Hours | AI Saving % | AI-Adj Hours | With Contingency | Days Equiv. | Tier
0 | 0% | 0 | 0 | 0
INFORMATICA EFFORT (Hours — by Environment)
Metric | Dev (hrs) | Test (hrs) | Prod (hrs) | Total (all envs)
Job Count | 0 | — | — | —
JDBC Update | 0 | 0 | 0 | 0
ENVIRONMENT EFFORT BREAKDOWN (Hours)
Layer | Dev (hrs) | Test (hrs) | Prod (hrs)
Data Migration | 0 | 0 | 0
ETL (Glue) | 0 | 0 | 0
Total (all) | 0 | 0 | 0
SQL SERVER REPLICATION
Replication Type | ⬆ ENTER
Replication Articles (Trans+Merge) | ▼ Select
Snapshot Publications | ⬆ ENTER

## 📅 Wave Plan
Activity | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9
PHASE 0 — FOUNDATION & PLANNING
AWS Landing Zone, VPC, Direct Connect | █ | █
S3 Backup Bucket + IAM + DMS Instance Setup | █
SCT Assessment (all 29 apps) | █ | █
SSIS Inventory + SSRS Audit | █ | █
Reusable Artefact Creation (scripts/templates) | █ | █
AWS CDK Pipeline + Secrets Manager Setup | █ | █
Team Training (RDS, Glue, CDK) | █ | █
PHASE 1 — WAVE 1: SIMPLE APPS (~9 apps)
Backup/Restore (T1 Apps) |  | █ | █
DMS CDC Setup + Monitoring |  | █ | █
SSIS → Glue (Low/Medium) |  |  | █ | █
SSRS EC2 Lift / QuickSight Build |  |  | █ | █
UAT + Smoke Test |  |  |  | █
Cutover & Go-Live (Wave 1) |  |  |  | █
PHASE 2 — WAVE 2: MODERATE APPS (~8 apps)
Backup/Restore + Differential Chain |  |  | █ | █
DMS CDC + Linked Server Remediation |  |  | █ | █
SSIS → Glue (Medium Complexity) |  |  |  | █ | █
SSRS EC2 + QuickSight |  |  |  | █ | █
Performance Testing (HammerDB) |  |  |  |  | █
Cutover & Go-Live (Wave 2) |  |  |  |  | █
PHASE 3 — WAVE 3: MOD-COMPLEX APPS (~8 apps)
Backup/Restore + S3 Transfer Accel. |  |  |  |  | █ | █
CLR Object Remediation |  |  |  |  | █ | █
SSIS → Glue (High Complexity) | [5 empty] | █ | █
Informatica JDBC Repoint (UAT) | [5 empty] | █ | █
SSRS Power BI + EC2 | [5 empty] | █ | █
UAT + Load Test | [6 empty] | █
Cutover & Go-Live (Wave 3) | [6 empty] | █
PHASE 4 — WAVE 4: COMPLEX APPS (~4 apps)
Differential Backup Chain + Restore | [6 empty] | █ | █
CLR + Linked Server Final Remediation | [6 empty] | █ | █
SSIS → Glue (High + Step Functions) | [6 empty] | █ | █
SSRS Power BI Executive + EC2 Ops | [7 empty] | █
Full Regression + 5-Day Parallel Run | [7 empty] | █ | █
Cutover & Go-Live (Wave 4) | [8 empty] | █
PHASE 5 — STABILISATION & CLOSURE
30-Day Hypercare Monitoring | [8 empty] | █
Reserved Instance Purchase | [8 empty] | █
On-Prem Decommission Planning | [7 empty] | █ | █
Final Documentation + BAU Handover | [8 empty] | █
Post-Migration Optimisation Review | [8 empty] | █
■ = Active in this month Bars are indicative; refine from App Inventory wave assignments

## ⚙️ Rate Card
DATABASE MIGRATION RATES (per unit)
Rate Driver | Base Rate | Unit | Notes
Schema/object base (per 100 GB) | 4 | hrs | AWS SCT review + object remediation; GHCP accelerated (was 0.5 days)
Data migration (per 100 GB) | 2.4 | hrs | DMS CDC setup + monitoring; backup/restore is the bulk method
Stored procedure remediation (per SP) | 4 | hrs | SQL dialect fixes for RDS-incompatible patterns; GHCP accelerated
View conversion (per view) | 1.6 | hrs | Mostly unchanged in backup/restore; flags only for linked server refs
Trigger conversion (per trigger) | 6.4 | hrs | Logic validation required post-restore
SQL Agent Job → EventBridge (per job) | 8 | hrs | GHCP generates CDK EventBridge constructs from Agent job definitions
Linked server removal (per linked svr) | 24 | hrs | Cross-DB query refactor; architect-guided pattern
CLR object rewrite (per CLR) | 40 | hrs | Rewrite to T-SQL stored proc or AWS Lambda; architect sign-off required
ETL MIGRATION — SSIS → AWS GLUE
Rate Driver | Base Rate | Unit | Notes
SSIS Low complexity (per package) | 4 | hrs | Simple copy; Glue Studio Visual ETL; GHCP generates (was 0.5 days)
SSIS Medium complexity (per package) | 8 | hrs | Transforms, lookups; Glue PySpark from template (was 1.0 day)
SSIS High complexity (per package) | 16 | hrs | Loops, dynamic SQL, error handling; Glue PySpark + Step Functions (was 2.0 days)
Informatica JDBC repoint (per app) | 0.8 | hrs | Config-only; JDBC connection string update in PowerCenter — no workflow change (was 0.1 days)
SSRS REPORTING MIGRATION
Rate Driver | Base Rate | Unit | Notes
SSRS → EC2 Lift & Shift (per report) | 1.6 | hrs | SSRS on Windows EC2; connection repointed to RDS endpoint
SSRS → AWS QuickSight (per report) | 12 | hrs | Dataset + visual rebuild in QuickSight; SPICE layer for performance
SSRS → Power BI (per report) | 8 | hrs | Power BI Desktop → Service; DirectQuery or Import to RDS
SSRS Decommission (per report) | 0.8 | hrs | Access log audit; archive and remove unused reports
INFRASTRUCTURE & DELIVERY
Rate Driver | Base Rate | Unit | Notes
AWS infra base per application | 80 | hrs | VPC, SG, RDS instance, Secrets Mgr, DMS, CloudWatch setup
AWS infra per 100 GB (DMS, storage) | 4 | hrs | DMS replication, S3 storage, CloudWatch alarms
QA effort multiplier (of tech total) | 0.28 | ratio | Schema + ETL + SSRS + infra; includes data integrity + load testing
PM effort multiplier | 0.12 | ratio | Status, risk, stakeholder, wave coordination
Solution Architect multiplier | 0.08 | ratio | Design governance, CLR patterns, cutover oversight
Hours per day (basis) | 8 | hrs | All effort calculations multiply days × 8 for hours
Contingency buffer | 15 | percent | Applied to AI-adjusted effort across all roles