## ✏️ SME Input
📋 INSTRUCTIONS: Fill in ORANGE cells only for your application. Grey cells are locked (auto-calculated or reference only). Dropdown cells have a pick-list — click the cell to see options. Contact the Migration PMO if you have questions.
Application Name | Wave / Release | DB Size (GB) | No. of Tables | No. of Stored Procs | No. of Views | No. of Triggers | SQL Agent Jobs | Linked Servers | CLR Objects | SSIS Packages | SSRS Reports | Informatica Workflows/Jobs (No workflow change — enter count) | SSIS Complexity | SSRS Strategy | SME Notes / Risks | Informatica Job Count | Replication Articles (Trans+Merge) | Snapshot Publications | Replication Type
Reference | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER count | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ ENTER | ⬆ Dropdown
Order Management System | Wave 2 | 450 | 120 | 85 | 45 | 12 | 8 | 2 | 3 | 18 | 22 | 5 | High | EC2 (Lift & Shift) |  | 5 | 8 | 0 | Transactional
Billing Engine | Wave 2 | 820 | 200 | 140 | 60 | 18 | 15 | 4 | 6 | 32 | 35 | 12 | High | EC2 (Lift & Shift) |  | 12 | 15 | 2 | Transactional
Customer Portal DB | Wave 1 | 180 | 80 | 45 | 30 | 5 | 3 | 0 | 0 | 8 | 10 | 0 | Medium | AWS QuickSight |  | 0 | 0 | 0 | None
Provisioning System | Wave 2 | 650 | 150 | 110 | 55 | 14 | 10 | 3 | 2 | 24 | 18 | 8 | High | EC2 (Lift & Shift) |  | 8 | 6 | 0 | Transactional
Revenue Assurance | Wave 4 | 1200 | 280 | 190 | 90 | 22 | 20 | 6 | 8 | 40 | 50 | 20 | High | EC2 (Lift & Shift) |  | 20 | 20 | 3 | Mixed
Fraud Management | Wave 2 | 340 | 95 | 65 | 35 | 8 | 6 | 1 | 4 | 15 | 12 | 3 | Medium | Power BI |  | 3 | 4 | 0 | Transactional
Network Inventory DB | Wave 2 | 560 | 130 | 95 | 48 | 10 | 9 | 2 | 1 | 20 | 16 | 6 | Medium | AWS QuickSight |  | 6 | 5 | 0 | Transactional
CRM Integration DB | Wave 1 | 220 | 75 | 50 | 28 | 6 | 4 | 0 | 0 | 10 | 8 | 2 | Medium | AWS QuickSight |  | 2 | 2 | 0 | None
Product Catalogue | Wave 1 | 90 | 45 | 30 | 20 | 3 | 2 | 0 | 0 | 4 | 5 | 0 | Low | AWS QuickSight |  | 0 | 0 | 0 | None
Mediation Platform | Wave 3 | 780 | 180 | 125 | 65 | 16 | 12 | 3 | 5 | 28 | 20 | 10 | High | EC2 (Lift & Shift) |  | 10 | 10 | 0 | Transactional
Interconnect Billing | Wave 2 | 420 | 110 | 80 | 40 | 9 | 7 | 2 | 2 | 16 | 14 | 4 | Medium | EC2 (Lift & Shift) |  | 4 | 4 | 0 | Transactional
Roaming Settlement | Wave 2 | 390 | 100 | 72 | 38 | 8 | 6 | 1 | 3 | 14 | 12 | 5 | Medium | EC2 (Lift & Shift) |  | 5 | 3 | 0 | Transactional
Dunning & Collections | Wave 1 | 250 | 85 | 58 | 32 | 7 | 5 | 0 | 1 | 10 | 15 | 2 | Medium | Power BI |  | 2 | 2 | 0 | None
Tax & Compliance DB | Wave 2 | 310 | 90 | 68 | 36 | 8 | 7 | 1 | 0 | 12 | 25 | 3 | Medium | EC2 (Lift & Shift) |  | 3 | 2 | 0 | Transactional
Contract Management | Wave 1 | 160 | 65 | 42 | 25 | 4 | 3 | 0 | 0 | 6 | 8 | 0 | Low | AWS QuickSight |  | 0 | 0 | 0 | None
Usage Rating Engine | Wave 3 | 920 | 210 | 155 | 70 | 20 | 16 | 4 | 7 | 35 | 28 | 15 | High | EC2 (Lift & Shift) |  | 15 | 12 | 2 | Transactional
Wholesale Billing | Wave 3 | 480 | 125 | 90 | 50 | 11 | 8 | 2 | 3 | 18 | 20 | 6 | High | EC2 (Lift & Shift) |  | 6 | 6 | 0 | Transactional
Partner Portal DB | Wave 1 | 140 | 55 | 35 | 22 | 3 | 2 | 0 | 0 | 5 | 6 | 0 | Low | AWS QuickSight |  | 0 | 0 | 0 | None
Workforce Management | Wave 2 | 200 | 72 | 48 | 28 | 5 | 4 | 0 | 0 | 8 | 10 | 1 | Medium | AWS QuickSight |  | 1 | 1 | 0 | None
Service Activation | Wave 2 | 370 | 105 | 75 | 42 | 9 | 7 | 1 | 2 | 14 | 12 | 4 | Medium | EC2 (Lift & Shift) |  | 4 | 4 | 0 | Transactional
Trouble Ticketing DB | Wave 2 | 230 | 80 | 55 | 30 | 6 | 4 | 0 | 0 | 9 | 8 | 1 | Medium | AWS QuickSight |  | 1 | 1 | 0 | None
SLA Management | Wave 2 | 180 | 68 | 45 | 26 | 5 | 3 | 0 | 0 | 7 | 14 | 0 | Medium | AWS QuickSight |  | 0 | 1 | 0 | None
Analytics Data Mart | Wave 4 | 1800 | 350 | 80 | 120 | 8 | 18 | 5 | 0 | 15 | 60 | 0 | High | Power BI |  | 0 | 0 | 0 | None
Regulatory Reporting DB | Wave 3 | 290 | 88 | 62 | 34 | 7 | 6 | 1 | 0 | 10 | 30 | 2 | Medium | EC2 (Lift & Shift) |  | 2 | 3 | 0 | Snapshot
Campaign Management | Wave 1 | 170 | 60 | 40 | 24 | 4 | 3 | 0 | 0 | 6 | 8 | 0 | Low | AWS QuickSight |  | 0 | 0 | 0 | None
Equipment Inventory | Wave 1 | 130 | 50 | 32 | 18 | 3 | 2 | 0 | 0 | 4 | 5 | 0 | Low | AWS QuickSight |  | 0 | 0 | 0 | None
Payment Gateway DB | Wave 3 | 410 | 115 | 82 | 44 | 10 | 8 | 2 | 2 | 16 | 10 | 5 | Medium | EC2 (Lift & Shift) |  | 5 | 5 | 0 | Transactional
Reporting Hub | Wave 4 | 680 | 160 | 55 | 85 | 6 | 10 | 2 | 0 | 8 | 75 | 0 | High | Power BI |  | 0 | 0 | 0 | None
MDM Master Data DB | Wave 4 | 520 | 140 | 98 | 52 | 12 | 9 | 3 | 1 | 18 | 22 | 7 | High | EC2 (Lift & Shift) |  | 7 | 8 | 1 | Transactional
TOTALS (auto) | 0 | 13340 | 3483 | 2207 | 1292 | 259 | 217 | 45 | 50 | 430 | 578 | 121 |  |  |  | 121 | 122 | 8

## 📋 App Effort Detail
Formulas auto-calculate from SME Input sheet values. Orange = SME editable input. Green = calculated output. Hours = Days × 8. AI saving applied per role. Contingency = AI-adj × (1 + buffer%).
APP IDENTITY |  | DATABASE PROFILE |  |  |  |  | SQL OBJECT INVENTORY | [5 empty] | ETL & REPORTING |  |  | EFFORT TOTALS (hours) | [9 empty] | INFORMATICA EFFORT (hrs) |  |  |  |  | ENVIRONMENT BREAKDOWN — Data & ETL (hrs) | [5 empty] | TOTAL BY ENV (hrs)
Application Name | Tier (Auto) | DB Size (GB) | Tables | Stored Procs | Views | Triggers | SQL Agent Jobs | Linked Servers | CLR Objects | SSIS Packages | SSRS Reports | Informatica Workflows/Jobs (No workflow change — count for JDBC) | SSIS Complexity | SSRS Strategy | Wave | Gross Hours | AI-Adj Hours | Hours w/ Contingency | [7 empty] | Informatica Job Count | Inform. Dev hrs | Inform. Test hrs | Inform. Prod hrs | Inform. Total hrs | Data Dev hrs | Data Test hrs | Data Prod hrs | ETL Dev hrs | ETL Test hrs | ETL Prod hrs | Total Dev hrs | Total Test hrs | Total Prod hrs
Label/Formula | Label/Formula | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | ⬆ Input | Formula | Formula | Formula | [7 empty] | Ref SME | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula | Formula
Order Management System | T1 Simple | 450 | 120 | 85 | 45 | 12 | 8 | 2 | 3 | 18 | 22 | 5 | High | EC2 (Lift & Shift) | Wave 2 | 1743.584 | 1271.2112 | 1461.8929 | 93.664 | 760.4 | 288 | 35.2 | 98 | 327.824 | 140.496 | 5 | 3.75 | 3.75 | 3.75 | 11.25 | 299.84 | 299.84 | 149.92 | 144 | 100.8 | 43.2 | 725.6636 | 682.4636 | 335.9068 | 8 | 0 | Transactional
Billing Engine | T2 Moderate | 820 | 200 | 140 | 60 | 18 | 15 | 4 | 6 | 32 | 35 | 12 | High | EC2 (Lift & Shift) | Wave 2 | 2921.1904 | 2130.9267 | 2450.5657 | 156.8384 | 1299.36 | 512 | 56 | 112.8 | 548.9344 | 235.2576 | 12 | 9 | 9 | 9 | 27 | 511.872 | 511.872 | 255.936 | 256 | 179.2 | 76.8 | 1220.8042 | 1144.0042 | 563.7021 | 15 | 2 | Transactional
Customer Portal DB | T1 Simple | 180 | 80 | 45 | 30 | 5 | 3 | 0 | 0 | 8 | 10 | 0 | Medium | AWS QuickSight | Wave 1 | 843.0656 | 621.2141 | 714.3962 | 45.3376 | 299.84 | 64 | 120 | 87.2 | 158.6816 | 68.0064 | 0 | 0 | 0 | 0 | 0 | 118.208 | 118.208 | 59.104 | 32 | 22.4 | 9.6 | 341.8982 | 332.2982 | 164.5491 | 0 | 0 | None
Provisioning System | T2 Moderate | 650 | 150 | 110 | 55 | 14 | 10 | 3 | 2 | 24 | 18 | 8 | High | EC2 (Lift & Shift) | Wave 2 | 2102.4 | 1533.24 | 1763.226 | 112.8 | 906.8 | 384 | 28.8 | 106 | 394.8 | 169.2 | 8 | 6 | 6 | 6 | 18 | 356.48 | 356.48 | 178.24 | 192 | 134.4 | 57.6 | 879.12 | 821.52 | 404.16 | 6 | 0 | Transactional
Revenue Assurance | T3 Complex | 1200 | 280 | 190 | 90 | 22 | 20 | 6 | 8 | 40 | 50 | 20 | High | EC2 (Lift & Shift) | Wave 4 | 3867.328 | 2819.7504 | 3242.713 | 207.488 | 1774.4 | 640 | 80 | 128 | 726.208 | 311.232 | 20 | 15 | 15 | 15 | 45 | 698.24 | 698.24 | 349.12 | 320 | 224 | 96 | 1614.4112 | 1518.4112 | 750.7056 | 20 | 3 | Mixed
Fraud Management | T1 Simple | 340 | 95 | 65 | 35 | 8 | 6 | 1 | 4 | 15 | 12 | 3 | Medium | Power BI | Wave 2 | 1385.3888 | 1011.4278 | 1163.142 | 74.4448 | 629.12 | 120 | 96 | 93.6 | 260.5568 | 111.6672 | 3 | 2.25 | 2.25 | 2.25 | 6.75 | 248.384 | 248.384 | 124.192 | 60 | 42 | 18 | 565.1415 | 547.1415 | 271.6958 | 4 | 0 | Transactional
Network Inventory DB | T2 Moderate | 560 | 130 | 95 | 48 | 10 | 9 | 2 | 1 | 20 | 16 | 6 | Medium | AWS QuickSight | Wave 2 | 1746.5792 | 1282.5946 | 1474.9837 | 93.6832 | 730.08 | 160 | 192 | 102.4 | 327.8912 | 140.5248 | 6 | 4.5 | 4.5 | 4.5 | 13.5 | 286.656 | 286.656 | 143.328 | 80 | 56 | 24 | 713.7557 | 689.7557 | 343.1278 | 5 | 0 | Transactional
CRM Integration DB | T1 Simple | 220 | 75 | 50 | 28 | 6 | 4 | 0 | 0 | 10 | 8 | 2 | Medium | AWS QuickSight | Wave 1 | 884.5184 | 649.3971 | 746.8067 | 47.5264 | 334.56 | 80 | 96 | 88.8 | 166.3424 | 71.2896 | 2 | 1.5 | 1.5 | 1.5 | 4.5 | 131.712 | 131.712 | 65.856 | 40 | 28 | 12 | 361.1954 | 349.1954 | 173.3477 | 2 | 0 | None
Product Catalogue | T1 Simple | 90 | 45 | 30 | 20 | 3 | 2 | 0 | 0 | 4 | 5 | 0 | Low | AWS QuickSight | Wave 1 | 523.9488 | 383.4358 | 440.9512 | 28.2048 | 195.12 | 16 | 60 | 83.6 | 98.7168 | 42.3072 | 0 | 0 | 0 | 0 | 0 | 77.184 | 77.184 | 38.592 | 8 | 5.6 | 2.4 | 210.3155 | 207.9155 | 103.5578 | 0 | 0 | None
Mediation Platform | T2 Moderate | 780 | 180 | 125 | 65 | 16 | 12 | 3 | 5 | 28 | 20 | 10 | High | EC2 (Lift & Shift) | Wave 3 | 2557.6896 | 1864.0173 | 2143.6199 | 137.2416 | 1143.04 | 448 | 32 | 111.2 | 480.3456 | 205.8624 | 10 | 7.5 | 7.5 | 7.5 | 22.5 | 449.728 | 449.728 | 224.864 | 224 | 156.8 | 67.2 | 1067.8878 | 1000.6878 | 492.8939 | 10 | 0 | Transactional
Interconnect Billing | T1 Simple | 420 | 110 | 80 | 40 | 9 | 7 | 2 | 2 | 16 | 14 | 4 | Medium | EC2 (Lift & Shift) | Wave 2 | 1341.6064 | 972.9555 | 1118.8988 | 71.9744 | 662.56 | 128 | 22.4 | 96.8 | 251.9104 | 107.9616 | 4 | 3 | 3 | 3 | 9 | 260.992 | 260.992 | 130.496 | 64 | 44.8 | 19.2 | 548.4106 | 529.2106 | 262.9053 | 4 | 0 | Transactional
Roaming Settlement | T1 Simple | 390 | 100 | 72 | 38 | 8 | 6 | 1 | 3 | 14 | 12 | 5 | Medium | EC2 (Lift & Shift) | Wave 2 | 1258.1248 | 911.8326 | 1048.6075 | 67.5008 | 626.32 | 112 | 19.2 | 95.6 | 236.2528 | 101.2512 | 5 | 3.75 | 3.75 | 3.75 | 11.25 | 246.784 | 246.784 | 123.392 | 56 | 39.2 | 16.8 | 514.4559 | 497.6559 | 247.903 | 3 | 0 | Transactional
Dunning & Collections | T1 Simple | 250 | 85 | 58 | 32 | 7 | 5 | 0 | 1 | 10 | 15 | 2 | Medium | Power BI | Wave 1 | 1062.72 | 779.896 | 896.8804 | 57.12 | 430 | 80 | 120 | 90 | 199.92 | 85.68 | 2 | 1.5 | 1.5 | 1.5 | 4.5 | 169.6 | 169.6 | 84.8 | 40 | 28 | 12 | 432.188 | 420.188 | 208.844 | 2 | 0 | None
Tax & Compliance DB | T1 Simple | 310 | 90 | 68 | 36 | 8 | 7 | 1 | 0 | 12 | 25 | 3 | Medium | EC2 (Lift & Shift) | Wave 2 | 1056.8192 | 768.4266 | 883.6905 | 56.7232 | 488.08 | 96 | 40 | 92.4 | 198.5312 | 85.0848 | 3 | 2.25 | 2.25 | 2.25 | 6.75 | 192.256 | 192.256 | 96.128 | 48 | 33.6 | 14.4 | 431.6017 | 417.2017 | 207.3258 | 2 | 0 | Transactional
Contract Management | T1 Simple | 160 | 65 | 42 | 25 | 4 | 3 | 0 | 0 | 6 | 8 | 0 | Low | AWS QuickSight | Wave 1 | 705.7152 | 518.0794 | 595.7913 | 37.9392 | 271.68 | 24 | 96 | 86.4 | 132.7872 | 56.9088 | 0 | 0 | 0 | 0 | 0 | 107.136 | 107.136 | 53.568 | 12 | 8.4 | 3.6 | 283.1501 | 279.5501 | 139.175 | 0 | 0 | None
Usage Rating Engine | T2 Moderate | 920 | 210 | 155 | 70 | 20 | 16 | 4 | 7 | 35 | 28 | 15 | High | EC2 (Lift & Shift) | Wave 3 | 3195.9104 | 2329.6627 | 2679.1121 | 171.5584 | 1444.96 | 560 | 44.8 | 116.8 | 600.4544 | 257.3376 | 15 | 11.25 | 11.25 | 11.25 | 33.75 | 569.152 | 569.152 | 284.576 | 280 | 196 | 84 | 1336.7822 | 1252.7822 | 618.0161 | 12 | 2 | Transactional
Wholesale Billing | T1 Simple | 480 | 125 | 90 | 50 | 11 | 8 | 2 | 3 | 18 | 20 | 6 | High | EC2 (Lift & Shift) | Wave 3 | 1776.1536 | 1294.2925 | 1488.4364 | 95.3856 | 784.64 | 288 | 32 | 99.2 | 333.8496 | 143.0784 | 6 | 4.5 | 4.5 | 4.5 | 13.5 | 309.248 | 309.248 | 154.624 | 144 | 100.8 | 43.2 | 739.1534 | 695.9534 | 343.0267 | 6 | 0 | Transactional
Partner Portal DB | T1 Simple | 140 | 55 | 35 | 22 | 3 | 2 | 0 | 0 | 5 | 6 | 0 | Low | AWS QuickSight | Wave 1 | 590.8608 | 432.9174 | 497.8551 | 31.7568 | 222.72 | 20 | 72 | 85.6 | 111.1488 | 47.6352 | 0 | 0 | 0 | 0 | 0 | 87.744 | 87.744 | 43.872 | 10 | 7 | 3 | 237.0003 | 234.0003 | 116.5002 | 0 | 0 | None
Workforce Management | T1 Simple | 200 | 72 | 48 | 28 | 5 | 4 | 0 | 0 | 8 | 10 | 1 | Medium | AWS QuickSight | Wave 2 | 871.488 | 641.6384 | 737.8842 | 46.848 | 318.4 | 64 | 120 | 88 | 163.968 | 70.272 | 1 | 0.75 | 0.75 | 0.75 | 2.25 | 125.44 | 125.44 | 62.72 | 32 | 22.4 | 9.6 | 353.8252 | 344.2252 | 170.8876 | 1 | 0 | None
Service Activation | T1 Simple | 370 | 105 | 75 | 42 | 9 | 7 | 1 | 2 | 14 | 12 | 4 | Medium | EC2 (Lift & Shift) | Wave 2 | 1243.9104 | 901.6227 | 1036.8661 | 66.7584 | 617.36 | 112 | 19.2 | 94.8 | 233.6544 | 100.1376 | 4 | 3 | 3 | 3 | 9 | 243.392 | 243.392 | 121.696 | 56 | 39.2 | 16.8 | 508.2122 | 491.4122 | 244.4061 | 4 | 0 | Transactional
Trouble Ticketing DB | T1 Simple | 230 | 80 | 55 | 30 | 6 | 4 | 0 | 0 | 9 | 8 | 1 | Medium | AWS QuickSight | Wave 2 | 908.7936 | 666.4445 | 766.4112 | 48.8256 | 358.64 | 72 | 96 | 89.2 | 170.8896 | 73.2384 | 1 | 0.75 | 0.75 | 0.75 | 2.25 | 141.248 | 141.248 | 70.624 | 36 | 25.2 | 10.8 | 369.2594 | 358.4594 | 177.8047 | 1 | 0 | None
SLA Management | T1 Simple | 180 | 68 | 45 | 26 | 5 | 3 | 0 | 0 | 7 | 14 | 0 | Medium | AWS QuickSight | Wave 2 | 892.7936 | 661.3645 | 760.5692 | 48.0256 | 293.44 | 56 | 168 | 87.2 | 168.0896 | 72.0384 | 0 | 0 | 0 | 0 | 0 | 115.648 | 115.648 | 57.824 | 28 | 19.6 | 8.4 | 360.9894 | 352.5894 | 174.8947 | 1 | 0 | None
Analytics Data Mart | T3 Complex | 1800 | 350 | 80 | 120 | 8 | 18 | 5 | 0 | 15 | 60 | 0 | High | Power BI | Wave 4 | 2728.512 | 2020.7616 | 2323.8758 | 145.152 | 985.6 | 240 | 480 | 152 | 508.032 | 217.728 | 0 | 0 | 0 | 0 | 0 | 376.96 | 376.96 | 188.48 | 120 | 84 | 36 | 1098.1248 | 1062.1248 | 525.0624 | 0 | 0 | None
Regulatory Reporting DB | T1 Simple | 290 | 88 | 62 | 34 | 7 | 6 | 1 | 0 | 10 | 30 | 2 | Medium | EC2 (Lift & Shift) | Wave 3 | 979.8528 | 713.103 | 820.0685 | 52.5888 | 444.72 | 80 | 48 | 91.6 | 184.0608 | 78.8832 | 2 | 1.5 | 1.5 | 1.5 | 4.5 | 175.104 | 175.104 | 87.552 | 40 | 28 | 12 | 398.6571 | 386.6571 | 192.0786 | 3 | 0 | Snapshot
Campaign Management | T1 Simple | 170 | 60 | 40 | 24 | 4 | 3 | 0 | 0 | 6 | 8 | 0 | Low | AWS QuickSight | Wave 1 | 693.2864 | 509.1395 | 585.5104 | 37.2544 | 262.96 | 24 | 96 | 86.8 | 130.3904 | 55.8816 | 0 | 0 | 0 | 0 | 0 | 103.552 | 103.552 | 51.776 | 12 | 8.4 | 3.6 | 278.0826 | 274.4826 | 136.6413 | 0 | 0 | None
Equipment Inventory | T1 Simple | 130 | 50 | 32 | 18 | 3 | 2 | 0 | 0 | 4 | 5 | 0 | Low | AWS QuickSight | Wave 1 | 538.1696 | 393.6413 | 452.6875 | 28.9216 | 203.44 | 16 | 60 | 85.2 | 101.2256 | 43.3824 | 0 | 0 | 0 | 0 | 0 | 80.128 | 80.128 | 40.064 | 8 | 5.6 | 2.4 | 215.6198 | 213.2198 | 106.2099 | 0 | 0 | None
Payment Gateway DB | T1 Simple | 410 | 115 | 82 | 44 | 10 | 8 | 2 | 2 | 16 | 10 | 5 | Medium | EC2 (Lift & Shift) | Wave 3 | 1372.9792 | 994.8746 | 1144.1057 | 73.6832 | 690.48 | 128 | 16 | 96.4 | 257.8912 | 110.5248 | 5 | 3.75 | 3.75 | 3.75 | 11.25 | 272.256 | 272.256 | 136.128 | 64 | 44.8 | 19.2 | 561.8057 | 542.6057 | 269.9778 | 5 | 0 | Transactional
Reporting Hub | T2 Moderate | 680 | 160 | 55 | 85 | 6 | 10 | 2 | 0 | 8 | 75 | 0 | High | Power BI | Wave 4 | 2089.9776 | 1568.6157 | 1803.908 | 112.0896 | 582.24 | 128 | 600 | 107.2 | 392.3136 | 168.1344 | 0 | 0 | 0 | 0 | 0 | 226.368 | 226.368 | 113.184 | 64 | 44.8 | 19.2 | 842.263 | 823.063 | 408.3315 | 0 | 0 | None
MDM Master Data DB | T2 Moderate | 520 | 140 | 98 | 52 | 12 | 9 | 3 | 1 | 18 | 22 | 7 | High | EC2 (Lift & Shift) | Wave 4 | 1778.5344 | 1296.3059 | 1490.7518 | 95.4624 | 781.76 | 288 | 35.2 | 100.8 | 334.1184 | 143.1936 | 7 | 5.25 | 5.25 | 5.25 | 15.75 | 307.712 | 307.712 | 153.856 | 144 | 100.8 | 43.2 | 740.4718 | 697.2718 | 344.0609 | 8 | 1 | Transactional
TOTALS |  | 13340 | 3483 | 2207 | 1292 | 259 | 217 | 45 | 50 | 430 | 578 | 121 |  |  |  | 43661.9008 | 31942.7894 | 36734.2079 | 2342.7968 | 18542.72 | 5228 | 2980.8 | 2853.6 | 8199.7888 | 3514.1952 | 121 | 90.75 | 90.75 | 90.75 | 272.25 | 7289.024 | 7289.024 | 3644.512 | 2614 | 1829.8 | 784.2 | 17950.2463 | 17166.0463 | 8497.6982 | 122 | 8

## 📊 Dashboard
29 Applications ¦ SSIS→AWS Glue ¦ Informatica: No Change ¦ 9-Month Rolling ¦ GHCP + Devin AI
PROGRAMME ASSUMPTIONS (Orange = editable inputs)
Hours per Day (basis) | 8
Programme Timeline (months) | 9
AI Saving % — Schema/Code/DBA | 30
AI Saving % — ETL (SSIS→Glue) | 25
AI Saving % — SSRS / BI Work | 20
AI Saving % — Testing & QA | 20
Contingency Buffer % | 15
Parallel Apps in Flight (wave) | 4
PROGRAMME TOTALS (Live — recalculates from App Effort Detail)
Total Apps | Total DB (GB) | Gross Hours | AI-Adj Hours | Hours w/ Conting. | FTE Equiv. | Days Equiv.
29 | 13340 | 43661.9008 | 31942.7894 | 36734.2079 | 25.5099 | 4591.776
EFFORT BY ROLE (Hours)
Role | Gross Hours | AI Saving % | AI-Adj Hours | With Contingency | FTE Equiv. | % of Total
Solution Architect | 2342.7968 | 30 | 1639.9578 | 1885.9514 | 1.3097 | 5.134%
DBA / Database Engineer | 18542.72 | 30 | 12979.904 | 14926.8896 | 10.3659 | 40.63%
ETL Developer (SSIS→Glue) | 5228 | 25 | 3921 | 4509.15 | 3.1314 | 12.28%
SSRS / BI Developer | 2980.8 | 20 | 2384.64 | 2742.336 | 1.9044 | 7.465%
AWS Infra / DevOps | 2853.6 | 30 | 1997.52 | 2297.148 | 1.5952 | 6.253%
QA / Test Engineer | 8199.7888 | 20 | 6559.831 | 7543.8057 | 5.2388 | 20.54%
Project Manager | 3514.1952 | 30 | 2459.9366 | 2828.9271 | 1.9645 | 7.701%
TOTAL | 43661.9008 |  | 31942.7894 | 36734.2079 | 25.5099 | 100%
LEGEND
● Orange = Editable assumption — change to model different scenarios
● Blue = Locked programme parameter
● Green = Calculated output (hours incl. AI saving + contingency)
INFORMATICA EFFORT (Connection update per job × 3 environments)
Total Jobs | Dev (hrs) | Test (hrs) | Prod (hrs) | All Envs (hrs)
121 | 90.75 | 90.75 | 90.75 | 272.25
TOTAL EFFORT BY ENVIRONMENT (All layers — hours)
Development (Dev RDS) | Test / UAT (Test RDS) | Production (Prod RDS) | Total All Environments
17950.2463 | 17166.0463 | 8497.6982 | 43613.9908
REPLICATION INVENTORY SUMMARY
Apps w/ Replication | Total Articles (Trans+Merge) | Total Snapshot Pubs | Transactional | Merge/Snapshot | None
16 | 122 | 8 | 14 | 2 | 13

## 🔍 App Pivot View
APPLICATION DRILL-DOWN VIEW — Select an application to see full effort breakdown
SELECT APPLICATION: | Order Management System
Click cell C5 to select a different application from the dropdown ▼
Matched Row (ref): | 8
APPLICATION PROFILE
Application Name | Order Management System
Migration Tier | T1 Simple
DB Size (GB) | 450
Wave / Release | Wave 2
SSIS Complexity | High
SSRS Strategy | EC2 (Lift & Shift)
SQL OBJECT INVENTORY
Tables | 120
Stored Procedures | 85
Views | 45
Triggers | 12
SQL Agent Jobs | 8
Linked Servers | 2
CLR Objects | 3
SSIS Packages | 18
SSRS Reports | 22
Informatica Workflows | 5
EFFORT BREAKDOWN (HOURS)
Role | Gross Hours | AI Saving % | AI-Adj Hours | w/ Contingency
Solution Architect | 93.664 | 30 | 65.5648 | 75.3995
DBA / DB Engineer | 760.4 | 30 | 532.28 | 612.122
ETL Dev (SSIS→Glue) | 288 | 25 | 216 | 248.4
SSRS / BI Developer | 35.2 | 20 | 28.16 | 32.384
AWS Infra / DevOps | 98 | 30 | 68.6 | 78.89
QA / Test Engineer | 327.824 | 20 | 262.2592 | 301.5981
Project Manager | 140.496 | 30 | 98.3472 | 113.0993
TOTAL (this app) | 1743.584 |  | 1271.2112 | 1461.8929
APPLICATION SUMMARY TOTALS
Gross Hours | AI Saving % | AI-Adj Hours | With Contingency | Days Equiv. | Tier
1743.584 | 27.09% | 1271.2112 | 1461.8929 | 182.7366 | T1 Simple
INFORMATICA EFFORT (Hours — by Environment)
Metric | Dev (hrs) | Test (hrs) | Prod (hrs) | Total (all envs)
Job Count | 5 | — | — | —
JDBC Update | 3.75 | 3.75 | 3.75 | 11.25
ENVIRONMENT EFFORT BREAKDOWN (Hours)
Layer | Dev (hrs) | Test (hrs) | Prod (hrs)
Data Migration | 299.84 | 299.84 | 149.92
ETL (Glue) | 144 | 100.8 | 43.2
Total (all) | 725.6636 | 682.4636 | 335.9068
SQL SERVER REPLICATION
Replication Type | Transactional
Replication Articles (Trans+Merge) | 8
Snapshot Publications | 0

## 📅 Wave Plan
Activity | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9
PHASE 0 — FOUNDATION & PLANNING
AWS Landing Zone, VPC, Direct Connect | █ | █
S3 Backup Bucket + IAM + DMS Instance Setup | █
SCT Assessment (all 29 apps) | █ | █
SSIS Inventory + SSRS Audit | █ | █
Reusable Artefact Creation (scripts/templates) | █ | █
AWS CDK Pipeline + Secrets Manager Setup | █ | █
Team Training (RDS, Glue, CDK) | █ | █
PHASE 1 — WAVE 1: SIMPLE APPS (~9 apps)
Backup/Restore (T1 Apps) |  | █ | █
DMS CDC Setup + Monitoring |  | █ | █
SSIS → Glue (Low/Medium) |  |  | █ | █
SSRS EC2 Lift / QuickSight Build |  |  | █ | █
UAT + Smoke Test |  |  |  | █
Cutover & Go-Live (Wave 1) |  |  |  | █
PHASE 2 — WAVE 2: MODERATE APPS (~8 apps)
Backup/Restore + Differential Chain |  |  | █ | █
DMS CDC + Linked Server Remediation |  |  | █ | █
SSIS → Glue (Medium Complexity) |  |  |  | █ | █
SSRS EC2 + QuickSight |  |  |  | █ | █
Performance Testing (HammerDB) |  |  |  |  | █
Cutover & Go-Live (Wave 2) |  |  |  |  | █
PHASE 3 — WAVE 3: MOD-COMPLEX APPS (~8 apps)
Backup/Restore + S3 Transfer Accel. |  |  |  |  | █ | █
CLR Object Remediation |  |  |  |  | █ | █
SSIS → Glue (High Complexity) | [5 empty] | █ | █
Informatica JDBC Repoint (UAT) | [5 empty] | █ | █
SSRS Power BI + EC2 | [5 empty] | █ | █
UAT + Load Test | [6 empty] | █
Cutover & Go-Live (Wave 3) | [6 empty] | █
PHASE 4 — WAVE 4: COMPLEX APPS (~4 apps)
Differential Backup Chain + Restore | [6 empty] | █ | █
CLR + Linked Server Final Remediation | [6 empty] | █ | █
SSIS → Glue (High + Step Functions) | [6 empty] | █ | █
SSRS Power BI Executive + EC2 Ops | [7 empty] | █
Full Regression + 5-Day Parallel Run | [7 empty] | █ | █
Cutover & Go-Live (Wave 4) | [8 empty] | █
PHASE 5 — STABILISATION & CLOSURE
30-Day Hypercare Monitoring | [8 empty] | █
Reserved Instance Purchase | [8 empty] | █
On-Prem Decommission Planning | [7 empty] | █ | █
Final Documentation + BAU Handover | [8 empty] | █
Post-Migration Optimisation Review | [8 empty] | █
■ = Active in this month Bars are indicative; refine from App Inventory wave assignments

## ⚙️ Rate Card
DATABASE MIGRATION RATES (per unit)
Rate Driver | Base Rate | Unit | Notes
Schema/object base (per 100 GB) | 4 | hrs | AWS SCT review + object remediation; GHCP accelerated (was 0.5 days)
Data migration (per 100 GB) | 2.4 | hrs | DMS CDC setup + monitoring; backup/restore is the bulk method
Stored procedure remediation (per SP) | 4 | hrs | SQL dialect fixes for RDS-incompatible patterns; GHCP accelerated
View conversion (per view) | 1.6 | hrs | Mostly unchanged in backup/restore; flags only for linked server refs
Trigger conversion (per trigger) | 6.4 | hrs | Logic validation required post-restore
SQL Agent Job → EventBridge (per job) | 8 | hrs | GHCP generates CDK EventBridge constructs from Agent job definitions
Linked server removal (per linked svr) | 24 | hrs | Cross-DB query refactor; architect-guided pattern
CLR object rewrite (per CLR) | 40 | hrs | Rewrite to T-SQL stored proc or AWS Lambda; architect sign-off required
ETL MIGRATION — SSIS → AWS GLUE
Rate Driver | Base Rate | Unit | Notes
SSIS Low complexity (per package) | 4 | hrs | Simple copy; Glue Studio Visual ETL; GHCP generates (was 0.5 days)
SSIS Medium complexity (per package) | 8 | hrs | Transforms, lookups; Glue PySpark from template (was 1.0 day)
SSIS High complexity (per package) | 16 | hrs | Loops, dynamic SQL, error handling; Glue PySpark + Step Functions (was 2.0 days)
Informatica JDBC repoint (per app) | 0.8 | hrs | Config-only; JDBC connection string update in PowerCenter — no workflow change (was 0.1 days)
SSRS REPORTING MIGRATION
Rate Driver | Base Rate | Unit | Notes
SSRS → EC2 Lift & Shift (per report) | 1.6 | hrs | SSRS on Windows EC2; connection repointed to RDS endpoint
SSRS → AWS QuickSight (per report) | 12 | hrs | Dataset + visual rebuild in QuickSight; SPICE layer for performance
SSRS → Power BI (per report) | 8 | hrs | Power BI Desktop → Service; DirectQuery or Import to RDS
SSRS Decommission (per report) | 0.8 | hrs | Access log audit; archive and remove unused reports
INFRASTRUCTURE & DELIVERY
Rate Driver | Base Rate | Unit | Notes
AWS infra base per application | 80 | hrs | VPC, SG, RDS instance, Secrets Mgr, DMS, CloudWatch setup
AWS infra per 100 GB (DMS, storage) | 4 | hrs | DMS replication, S3 storage, CloudWatch alarms
QA effort multiplier (of tech total) | 0.28 | ratio | Schema + ETL + SSRS + infra; includes data integrity + load testing
PM effort multiplier | 0.12 | ratio | Status, risk, stakeholder, wave coordination
Solution Architect multiplier | 0.08 | ratio | Design governance, CLR patterns, cutover oversight
Hours per day (basis) | 8 | hrs | All effort calculations multiply days × 8 for hours
Contingency buffer | 15 | percent | Applied to AI-adjusted effort across all roles