## Effort Calculator
Azure SQL MI → AWS Aurora PostgreSQL ¦ Migration Effort Calculator ¦ (Devin AI + GitHub Copilot)
Label / Object | Count (Input) | Manual Rate | AI Saving % | AI-Adj Rate | Hours (Sub) | SDLC +25% | Risk +10% | Total Hours
SECTION A — SCHEMA MIGRATION
Tables (SCT auto-convert + DBA review) | 500 | 0.40 hrs/table | 80% | 0.08
Views (SCT + manual T-SQL fix ~35%) | 250 | 1.50 hrs/view | 65% | 0.525
Indexes (clustered → B-tree strategy) | 200 | 0.50 hrs/group | 50% | 0.25
SPs — Simple CRUD (Devin autonomous) | 120 | 0.67 hrs/SP | 75% | 0.168
SPs — Business Logic (Devin+DBA review) | 105 | 1.50 hrs/SP | 65% | 0.525
SPs — Complex (DBA manual + GHCP) | 45 | 4.00 hrs/SP | 40% | 2.4
SPs — CLR Objects (full redesign) | 30 | 8.00 hrs/obj | 20% | 6.4
Functions — Scalar + TVF | 150 | 1.00 hrs/fn | 65% | 0.35
Triggers | 75 | 2.00 hrs/trigger | 45% | 1.1
SQL Agent Jobs | 50 | 2.00 hrs/job | 60% | 0.8
Security Roles / Logins | 40 | 0.50 hrs/role | 65% | 0.175
Devin Fine-Tuning (FIXED — mandatory) | FIXED | 80 hrs flat | 0% | 80 | 80
SCHEMA MIGRATION SUBTOTAL
SECTION B — DATA MIGRATION
App DB Size — Tier 1 (GB) | 2000 | 0.0040 hrs/GB | 20% | 0.0032
CDC Monitoring (weeks) | 12 | 8.00 hrs/week | 30% | 5.6
Warm History — Tier 2 (GB) | 12000 | 0.0030 hrs/GB | 40% | 0.0018
Cold Archive — Tier 3 (GB) | 35000 | 0.0010 hrs/GB | 50% | 0.0005
Tables to Validate | 500 | 0.25 hrs/table | 70% | 0.075
Cutover Rehearsals | 2 | 32 hrs/each | 20% | 25.6
DMS Infrastructure Setup (fixed) | 1 | 24 hrs flat | 40% | 14.4
DATA MIGRATION SUBTOTAL
SECTION C — ETL / PIPELINE MIGRATION
ADF Copy Activity pipelines | 45 | 2.0 hrs | 65% | 0.7
ADF Stored Proc Activity | 20 | 1.5 hrs | 65% | 0.525
ADF REST/Web Activity | 15 | 3.0 hrs | 55% | 1.35
ADF Data Flow — Simple | 30 | 4.0 hrs | 55% | 1.8
ADF Data Flow — Complex | 20 | 8.0 hrs | 40% | 4.8
Custom .NET Activity | 10 | 16.0 hrs | 35% | 10.4
Azure-specific pipelines | 8 | 24.0 hrs | 20% | 19.2
Azure Functions → Lambda | 15 | 8.0 hrs | 40% | 4.8
ETL Parallel Validation | 50 | 1.0 hrs | 55% | 0.45
MWAA + Glue Setup (fixed) | 1 | 24.0 hrs | 50% | 12
ETL MIGRATION SUBTOTAL
SECTION D — TESTING + PROJECT MANAGEMENT (all cells calculated)
Combined Base (Schema+Data+ETL Total)
Unit + Integration Testing (18% of base, 55% AI saving)
Performance Benchmarking (8% of base, 35% AI saving)
Regression — Ordering App (12% of base, 30% AI saving)
Regression — Billing App (15% of base, 30% AI saving)
UAT — Ordering (business users) (10% of base, 5% AI saving)
UAT — Billing (business users + SME) (14% of base, 5% AI saving)
Defect Management & Fix Cycles (15% of base, 40% AI saving)
Project Management & Governance (18% of base, 25% AI saving)
Knowledge Transfer & Training (8% of base, 40% AI saving)
TESTING + PM SUBTOTAL
GRAND TOTAL
Total Days (÷ 8 hrs/day)
Calendar Weeks (6-person team, 240 hrs/week)
SDLC Buffer +25%: iteration cycles, rework, review ¦ Risk Buffer +10%: telecom billing complexity ¦ Yellow cells = your inputs only

## Rate Reference
Rate Reference — Derivation Basis for All Effort Estimates
# | Object / Activity | Manual Rate | AI Saving % | AI-Adj Rate | Source / Basis | Calculation Logic | Key Assumption
1 | Tables (SCT auto-convert + DBA review) | 0.40 hrs/table | 80% | 0.08 hrs | AWS SCT benchmark + DBA review studies | SCT 95% auto. DBA reviews ~10 min/table. 0.4 × 0.20 = 0.08 hrs. | SCT handles DDL auto-conversion; DBA spot-checks constraints & defaults.
2 | Views (SCT + manual T-SQL fix ~35%) | 1.50 hrs/view | 65% | 0.525 hrs | SQL migration pattern library | 65% of views have T-SQL specifics needing manual rework. Devin fixes 65%. | Views using NOLOCK hints, TOP, SQL Server functions need manual rewrite.
3 | Indexes (clustered → B-tree strategy) | 0.50 hrs/group | 50% | 0.25 hrs | PostgreSQL B-tree equivalence docs | Clustered → PG heap + B-tree. DBA review 15 min/group after AI draft. | Covering indexes and filtered indexes need special attention.
4 | SPs — Simple CRUD (Devin autonomous) | 0.67 hrs/SP | 75% | 0.168 hrs | Nubank/Devin published benchmark | Nubank/Devin benchmark: 10 min/SP after fine-tuning = 0.67 hrs base. | Assumes Devin fine-tuned on PL/pgSQL patterns before sprint start.
5 | SPs — Business Logic (Devin+DBA review) | 1.50 hrs/SP | 65% | 0.525 hrs | Internal DBA time-and-motion study | Devin: 25 min/SP AI-adjusted. Full DBA review adds ~10 min/SP. | Contains billing rate lookups, conditional logic, temp tables.
6 | SPs — Complex (DBA manual + GHCP) | 4.00 hrs/SP | 40% | 2.4 hrs | Telecom DB migration case studies | DBA writes PL/pgSQL + GHCP inline. 90 min/SP AI-adjusted. | Linked server calls, dynamic SQL, multi-step transactions.
7 | SPs — CLR Objects (full redesign) | 8.00 hrs/obj | 20% | 6.4 hrs | PostgreSQL extension equivalence matrix | Architecture redesign. No direct PG equivalent. 6.4 hrs/object. | CLR replaced by custom PG extensions, PL/Python, or Lambda sidecars.
8 | Functions — Scalar + TVF | 1.00 hrs/fn | 65% | 0.35 hrs | T-SQL to PL/pgSQL function mapping guide | Scalar: direct rewrite. TVF: SRF in PG. Devin handles 65% autonomously. | Aggregates and window functions need manual verification.
9 | Triggers | 2.00 hrs/trigger | 45% | 1.1 hrs | DBA trigger migration benchmarks | INSTEAD OF triggers → PG rules or triggers. Devin drafts, DBA verifies. | Billing audit triggers are most complex — plan extra review time.
10 | SQL Agent Jobs | 2.00 hrs/job | 60% | 0.8 hrs | AWS EventBridge + Lambda patterns | Jobs → EventBridge Scheduler + Lambda. Devin generates boilerplate. | Multi-step jobs with notifications need custom Lambda error handling.
11 | Security Roles / Logins | 0.50 hrs/role | 65% | 0.175 hrs | AWS IAM + RDS role mapping guide | SQL Server logins → RDS IAM auth. Scripted by GHCP after template. | Windows-integrated logins require special Kerberos/IAM bridge setup.
12 | Devin Fine-Tuning (FIXED — mandatory) | 80 hrs flat | 0% | 80 hrs | Devin AI onboarding documentation | One-time cost: load SP corpus, run sample conversions, validate output quality. | Must be completed before any SP sprint. Amortized across all SP work.
13 | App DB Size — Tier 1 (GB) | 0.0040 hrs/GB | 20% | 0.0032 hrs/GB | AWS DMS throughput benchmarks | Full-load DMS at ~100 GB/hr. Monitoring & validation overhead adds 0.004 hrs/GB. | Tier 1 = active transactional data. Requires near-zero downtime cutover.
14 | CDC Monitoring (weeks) | 8.0 hrs/week | 30% | 5.6 hrs/wk | Telecom billing CDC case studies | 8 hrs/week base. GHCP dashboards save 30%. Telecom = 12–16 weeks. | High-TPS billing DBs need extended CDC validation before cutover.
15 | Warm History — Tier 2 (GB) | 0.0030 hrs/GB | 40% | 0.0018 hrs/GB | S3 bulk transfer benchmarks | Batch load via S3 + COPY. Less monitoring overhead than Tier 1. | Last 12 months of billing history. Needed for billing disputes.
16 | Cold Archive — Tier 3 (GB) | 0.0010 hrs/GB | 50% | 0.0005 hrs/GB | Glacier to Aurora migration patterns | Bulk S3 → Aurora load. Minimal validation. Scripts auto-generated. | 7+ year archive. Regulatory hold. Load once, read rarely.
17 | Tables to Validate | 0.25 hrs/table | 70% | 0.075 hrs | Data quality framework benchmarks | GHCP generates row-count, checksum, and sample comparison scripts. | Focus extra manual time on billing totals and order history tables.
18 | Cutover Rehearsals | 32 hrs/each | 20% | 25.6 hrs | Enterprise DB cutover runbook standards | Full dress rehearsal: stop writes, drain CDC, verify, cutover, smoke test. | Minimum 2 rehearsals recommended. Telecom billing = 3 recommended.
19 | DMS Infrastructure Setup (fixed) | 24 hrs flat | 40% | 14.4 hrs | AWS DMS setup documentation | VPC peering, replication instance sizing, endpoint config, IAM roles. | One-time. Reused across all DB migrations in the program.
20 | ADF Copy Activity pipelines | 2.0 hrs | 65% | 0.7 hrs | Devin ADF→Airflow benchmark | Devin reads ADF JSON → Airflow DAG → tests → PR. 42 min/pipeline. | Simple source→sink copies. Devin handles 95% of code generation.
21 | ADF Stored Proc Activity | 1.5 hrs | 65% | 0.525 hrs | MWAA DAG conversion patterns | SP call → Lambda invocation or Glue job. Devin generates wrapper. | Ensure SP has been migrated first before converting the pipeline.
22 | ADF REST/Web Activity | 3.0 hrs | 55% | 1.35 hrs | API integration migration benchmarks | REST calls to external APIs. Devin generates Python requests equivalent. | Check auth patterns — OAuth tokens may need refresh logic update.
23 | ADF Data Flow — Simple | 4.0 hrs | 55% | 1.8 hrs | Glue visual ETL migration guide | Simple transforms → Glue visual ETL or Spark job. Devin drafts. | Column mappings, type casts, simple filters. DBA validates output.
24 | ADF Data Flow — Complex | 8.0 hrs | 40% | 4.8 hrs | Telecom billing ETL complexity matrix | Billing flows = complex. Budget 6–8 hrs each. | Multi-join, lookup, conditional split. Manual DBA + GHCP rewrite.
25 | Custom .NET Activity | 16.0 hrs | 35% | 10.4 hrs | Lambda rewrite benchmark | Complete Python/Lambda rewrite. GHCP reduces typing 35%. | Business logic must be re-validated end-to-end. No shortcut.
26 | Azure-specific pipelines | 24.0 hrs | 20% | 19.2 hrs | Azure→AWS architecture mapping | Event Grid → EventBridge, Service Bus → SQS/SNS. Low AI coverage. | Azure-native services have no 1:1 AWS equivalent. Architecture review needed.
27 | Azure Functions → Lambda | 8.0 hrs | 40% | 4.8 hrs | Serverless migration playbook | Devin converts C# trigger → Python Lambda. Handler + IAM role included. | Billing event triggers are highest risk — validate trigger timing carefully.
28 | ETL Parallel Validation | 1.0 hrs | 55% | 0.45 hrs | Data reconciliation framework | GHCP generates parallel-run comparison scripts automatically. | Run old and new pipeline simultaneously. Compare row counts and totals.
29 | MWAA + Glue Setup (fixed) | 24.0 hrs | 50% | 12.0 hrs | AWS MWAA setup documentation | One-time MWAA environment + Glue catalog + IAM + VPC configuration. | Reused by all ETL pipelines. Must be done before any DAG deployment.

## How To Use
How To Use — Azure SQL MI → Aurora Migration Effort Calculator
Step | What To Do | Telecom-Specific Tip
Step 1 Get Inventory | Run AWS SCT against Azure SQL MI. Gets counts of: tables, views, SPs by complexity, functions, triggers, indexes, SQL Agent jobs, CLR objects. | Free tool. Connect read-only. Takes 2–4 hours on an enterprise-scale DB. Export the full SCT assessment report as HTML for evidence.
Step 2 Classify SPs | SCT rates SPs as: Simple (0–1 action items), Medium (2–5), Complex (6+). Map: Simple → Simple CRUD ¦ Medium → Business Logic ¦ Complex → Complex SP. | Billing SPs are usually Medium/Complex. Ordering SPs usually Simple/Medium. If >30% are Complex, budget extra DBA review sprint time.
Step 3 Count ADF Pipelines | Export ADF as ARM JSON template. Count by activityType field: Copy ¦ SqlServerStoredProcedure ¦ WebActivity ¦ ExecuteDataFlow ¦ DotNetActivity. | CLI: az datafactory pipeline list --factory-name <name> --resource-group <rg> Export to JSON and use grep/jq to count each activity type.
Step 4 Enter Yellow Cells | Go to Sheet 1 (Effort Calculator). Fill every YELLOW cell with your actual counts. Leave Section D alone — it calculates automatically from Sections A, B, C. | Start with schema counts (Section A), then GB volumes (Section B), then ETL pipeline counts (Section C). Section D self-populates.
Step 5 SP Mix Check | Default SP split: 40% Simple / 35% Business Logic / 15% Complex / 10% CLR. Adjust the counts in yellow cells based on your actual SCT output. | SCT auto-conversion rate >80% → lean Simple counts higher. SCT rate <70% → lean Complex counts higher. CLR > 10% of SPs = escalate.
Step 6 Adjust Data Volumes | Use Azure SQL MI database properties for actual GB sizes. If unknown: T1=20%, T2=30%, T3=50% of total volume as safe default. | CDC monitoring weeks = the single longest-running cost driver. Telecom billing high-TPS: plan 16 weeks minimum, not 12.
Step 7 Validate Output Mix | Sanity-check the output section percentages: Schema: 40–60% ¦ ETL: 25–35% ¦ Data: 10–20% ¦ Testing: 15–25%. | Schema >65% of total = CLR-heavy system. Flag for architecture review before quoting to the client. Do not proceed without DBA sign-off.
Step 8 Multi-DB Scale | For multiple databases: multiply Schema + ETL totals by DB count. Data migration already scales with GB — do NOT multiply those rows. | Shared SP libraries across DBs → don't multiply SP hours. Only multiply deployment and integration testing hours for multi-DB.
Step 9 Stakeholder Presentation | Lead with: "Total Hours = X. That's Y calendar weeks for a 6-person team. AI tooling is already built in — without AI this would be ~2× the hours." | Present 3 streams separately (Schema / Data / ETL). SDLC +25% and Risk +10% buffers are already included. DO NOT add additional buffers on top — this will double-count.